## HandoffRegister
# | Project | Outgoing owner | Incoming owner | Handoff date | Days to handoff | Status | Assets complete % | Open high risks | Client sign-off (Y/N) | Close gate
1 | EXAMPLE Website rebuild | You | Client team | 2026-11-01 |  | In progress |  |  | N
2 | EXAMPLE API integration | You | Agency B | 2026-11-15 |  | Not started |  |  | N
3
4
5
6
7
8
9
10
11
12
13
14
15
Formulas:
Days to handoff = IF(ISNUMBER([Handoff date]),[Handoff date]-TODAY(),"")

## ChecklistTemplate
Category | Item to transfer | Why it prevents a dispute
Code | Repository ownership moved to the client org; their admins, not yours | You keep write access and the 'transferred' claim is false
Code | Deploy keys / CI secrets reissued to the client and the old ones revoked | A live key in your hands is a latent security incident
Code | Staging and production reproduced by the incoming owner, live, on the call | A system they cannot run is not a system they own
Docs | Architecture notes: where everything lives and what depends on what | The next integrator starts from zero without this map
Docs | Runbook: deploy, roll back, restart, rotate credentials | An incident with no runbook becomes your unpaid emergency
Docs | Known-bugs list, written honestly, with severity | Undisclosed bugs become 'you hid this' arguments
Accounts | Hosting, DNS, analytics, error tracking: transfer ownership, never share a password | Shared passwords blur who changed what
Accounts | Every third-party API key reissued to a client-owned account | The client must not depend on your account staying open
Accounts | Billing for the above moved to the client, verified on the call | A silent recurring charge on your card is a dispute in month two
Money | Final invoice issued and payment terms stated in writing | Scope disputes are usually money disputes in disguise
Money | Outstanding expenses and retainer balance reconciled to the cent | Open money is the most common reason a handoff stalls
Data | Client data exported in an open format and delivered, not left in your tool | Data held hostage is the worst handoff failure
Data | Your working copies of client data deleted, confirmed and dated | A copy you forgot about is a privacy liability
Security | Every shared login replaced with a named account for each person | Anonymous shared logins can never be revoked or audited
Security | Access you still hold revoked or explicitly time-boxed | Standing access after handoff is a finding in any audit
People | Stakeholder introductions done with one line of context each | Names without context are useless to the receiver
People | One named decision-maker on each side, in writing | Two owners means no owner
Support | Support window: dates, what is covered, response time, and what costs extra | An undefined window becomes free, permanent, unlimited support

## AssetChecklist
Project | Category | Item | Access transferred (Y/N) | Verified by | Verified date | Where it lives (URL / path) | Proof note
EXAMPLE Website rebuild | Code | Repo ownership + deploy keys | N |  |  | github.com/…
EXAMPLE Website rebuild | Accounts | DNS registrar ownership | N |  |  | registrar login
EXAMPLE Website rebuild | Money | Final invoice issued | N

## RiskRegister
Project | Risk (what could go wrong) | Owner | Severity 1-5 | Likelihood 1-5 | Score (S×L) | Mitigation | Status (OPEN/CLOSED) | Due date | A score of 12 or more (S×L) counts as a HIGH risk and blocks the close gate until it is CLOSED.
EXAMPLE Website rebuild | DNS transfer fails during the window | You | 4 | 3 |  | Lower TTL 48h before; keep old host warm for 72h | OPEN | 2026-10-30

## Dashboard
KPI | Value | How it is computed
Projects tracked |  | Named rows on HandoffRegister
Projects READY TO CLOSE |  | Sign-off Y, assets 100%, no open high risks
Sign-offs collected |  | Client sign-off = Y
Open HIGH risks |  | Score >= 12 and status OPEN
Assets transferred (Y) |  | Access transferred = Y
Assets outstanding (N or blank) |  | Named checklist items not yet transferred
Transfer readiness % |  | Transferred ÷ named items
Next handoff in (days) |  | Smallest non-empty Days to handoff

## README
B12-002 Client Project Handoff Register — HOW TO USE
1) HandoffRegister: one row per project. Fill only the white cells. Blue cells compute (Days to handoff, Assets complete %, Open high risks, Close gate) and must not be overwritten. Yellow rows are EXAMPLES — overwrite or delete them.
2) AssetChecklist: add one row per item you are transferring, and set its Project name so it rolls up. Copy the exact items you need from ChecklistTemplate (Code, Docs, Accounts, Money, Data, Security, People, Support). Nothing counts as transferred until Access transferred = Y.
3) RiskRegister: log every handoff risk, score it Severity x Likelihood, and CLOSE the ones scoring 12 or more before you close the project. The close gate stays OPEN while a high risk is open.
4) Dashboard: reads the three sheets and shows transfer readiness, sign-offs, and the next handoff date. A project is 'READY TO CLOSE' only when its assets are 100%, it has no open high risks, and the client has signed off.
5) Use with the B12-002 PDF guide (the 45-minute session script and the copy-paste emails). This is a record-keeping tool, not legal advice.