## Deal_Tracker
Deal ID | Property Address | Side | Contract Date | Close Date | Days To Close | Status | Next Deadline | Next Deadline Date | Priority
D-01 | 1204 Maple Ave, Springfield | Buyer | 2026-09-02 | 2026-10-17 |  | Active | Inspection objection | 2026-09-12 | High
D-02 | 88 River Rd, Springfield | Seller | 2026-08-28 | 2026-10-02 | 35 | Pending Docs | Appraisal review | 2026-09-18 | Normal
D-03 | 15 Hillcrest Ln, Springfield | Buyer | 2026-09-05 | 2026-11-04 |  | Active | Loan commitment | 2026-10-10 | Normal
Notes: F2 and F4 compute days to close as close date minus contract date. Copy the F-column formula down for each new row. A8 counts deals entered. Use controlled Status words only: Active, Pending Docs, Clear to Close, Closed, On Hold. Sample rows are illustrative. Replace them with your files.

## Contingency_Log
Deal ID | Contingency Type | Deadline Date | Days Remaining | Status | Date Satisfied | Notes
D-01 | Inspection | 2026-09-12 |  |  |  | Sample row. Illustrative dates.
D-01 | Appraisal | 2026-09-26 | -2 | DUE SOON |  | Sample row. Illustrative dates.
D-02 | Loan | 2026-09-30 |  | ON TRACK |  | Sample row. Illustrative dates.
Notes: D2 computes days remaining as deadline minus today and refreshes on open. E2 flags SATISFIED, OVERDUE, DUE SOON within 7 days, or ON TRACK. Copy D and E formulas down for each new row. Apply your state day-counting rules before entering each deadline. Sample rows are illustrative.
Formulas:
Days Remaining = [Deadline Date]-TODAY()
Status = IF([Date Satisfied]<>"","SATISFIED",IF([Deadline Date]<TODAY(),"OVERDUE",IF([Deadline Date]<=TODAY()+7,"DUE SOON","ON TRACK")))

## Document_Checklist
Deal ID | Document | Required | Received | Date Received | Status
D-01 | Signed contract with addenda | Yes | Yes | 2026-09-02
D-01 | Inspection report | Yes | No
D-02 | Pre-approval letter | Yes | Yes | 2026-08-28 | OK
Notes: F2 and F3 flag required-but-unreceived documents as MISSING. Copy the F-column formula down for each new row. A9 counts open missing items. Sample rows are illustrative.

## Post_Close_Review
Deal ID | Contract Date | Close Date | Days To Close | What Slipped | Lesson | Follow-up Action | Follow-up Done
D-00 | 2026-06-01 | 2026-07-15 |  | Title ordered late | Order title within 24 hours of acceptance | Checklist rule added | Yes
D-00 | 2026-05-10 | 2026-06-20 | 41 | Appraisal returned late | Confirm expected return date in writing at order | Lender note filed | Yes
D-00 | 2026-04-03 | 2026-05-12 | 39 | HOA docs chased last week | Request HOA docs at acceptance | Template updated | No
Notes: D2 computes actual days to close as close minus contract. Copy down per closed deal. A8 averages sample durations. Complete within three business days of closing. Sample rows are illustrative.