## SAQ selector worksheet
Step | Question | Your answer (Yes/No) | If Yes go to | If No go to | Notes
1 | Do you handle card numbers on your own computers or network? | No | Step 3 | Step 2 | Illustrative row
2 | Do you use only a validated payment terminal supplied by your processor with no electronic card data stored? | Yes | Candidate path A | Step 3 | Illustrative row
3 | Do card numbers pass through or get stored on your website server? | No | Candidate path B | Step 4 | Illustrative row
4 | Did you record the answers with dates and who answered? | Yes | Done | Repeat Step 4 | Illustrative row
Notes: Work through every step in order. The result is a candidate path to discuss with your acquirer, not a final determination. Illustrative example rows are marked as illustrative.

## Scope inventory
Location or device | Card data present (Yes/No/Unknown) | How cards are handled here | Owner | Keep, change, or remove | Target date | Done (Yes/No)
Front counter terminal | No | Processor-supplied terminal, dial-out over phone line | Owner | Keep | 2026-10-15 | No
Back-office PC | Unknown | Staff sometimes open emailed reports from processor | Office manager | Change | 2026-10-22 | No
Old laptop in storage | Unknown | Retired in 2024, drive not wiped per log | Owner | Remove | 2026-10-30 | No
Notes: List every place cards could be handled, including old devices and email inboxes. Unknown means investigate, not ignore. Illustrative rows are examples only.

## Readiness log
Requirement reference | Requirement summary in plain language | Status (Not started/In progress/Ready for review/Confirmed) | Evidence location | Owner | Date last checked | Next check date
Req-01 | Change default passwords on payment equipment | In progress | Terminal setup file, drawer 2 | Office manager | 2026-09-20 | 2026-10-20
Req-02 | Limit who can access card handling areas | Not started | Door code list | Owner | 2026-09-20 | 2026-10-20
Req-03 | Review service provider list quarterly | Not started | Provider file | Owner | 2026-09-20 | 2026-12-20
Notes: Status values feed the summary formulas in H1 and H2. Confirmed means evidence was seen and filed, not that an outside party accepted it. Illustrative rows only.

## Incident-plan checklist
Checklist item | Done (Yes/No) | Owner | Date | Evidence or file name | Gap or follow-up
Suspected card incident contact numbers posted at counter | No | Owner |  | To be printed | Print and post by target date
Steps for isolating an affected terminal written down | No | Office manager |  | Template draft | Complete draft review
Annual review of this plan scheduled | No | Owner |  | Calendar entry pending | Add to renewal calendar
Notes: Tracks completion of the incident-response plan template. Each Yes should have a named evidence file. Illustrative rows only.

## Renewal calendar
Task | Frequency | Last done | Next due | Owner | Status (On time/Overdue/Not scheduled)
Review SAQ path with acquirer | Annual | 2026-03-01 | 2027-03-01 | Owner | On time
Review service provider list | Quarterly | 2026-09-01 | 2026-12-01 | Office manager | On time
Test incident contact list | Semiannual |  | 2026-10-15 | Owner | Not scheduled
Renew attestation paperwork | Annual | 2026-03-01 | 2027-03-01 | Owner | On time
Notes: Update Last done dates as tasks complete so Next due stays accurate. Overdue counts surface in G1. Illustrative rows only.