## Appointment no-show log
Date | Provider | Appointments booked | Confirmed (Yes replies) | No-shows | Same-day cancellations | Filled from waitlist
2026-09-07 | Provider A | 22 | 15 | 4 | 1 | 1
2026-09-08 | Provider B | 18 | 12 | 3 | 2 | 0
2026-09-09 | Provider A | 24 | 18 | 2 | 1 | 2
Notes: H1 is the no-show rate. H2 is the confirmation rate. H3 totals waitlist fills. Example rows are illustrative only.

## Message performance tracker
Week starting | Touch sent (7-day/48-hour/same-day) | Messages sent | YES replies | NO replies | No reply | Rescheduled after NO
2026-09-07 | 7-day | 60 | 35 | 5 | 20 | 3
2026-09-07 | 48-hour | 58 | 30 | 4 | 24 | 2
2026-09-07 | same-day | 55 | 20 | 2 | 33 | 1
Notes: One row per touch per week. H1/H2/H3 give reply mix. Example rows are illustrative only.

## Waitlist log
Date slot opened | Slot date and time | Provider | Patient reference code | Contacted (Yes/No) | Accepted (Yes/No/Declined) | Filled date | Staff initials
2026-09-08 | 2026-09-10 09:00 | Provider A | REF-1042 | Yes | Yes | 2026-09-08 | OM
2026-09-08 | 2026-09-10 11:30 | Provider B | REF-1043 | Yes | Declined |  | OM
2026-09-09 | 2026-09-11 14:00 | Provider A | REF-1044 | No |  |  | FR
Notes: Use reference codes, never patient names. I1 counts filled slots. I2 counts opened slots not yet contacted. Illustrative rows only.

## Reason-code summary
Reason code | Meaning | Count this month | Share of no-shows
R1 | Forgot appointment | 6
R2 | Transportation problem | 3
R3 | Work or school conflict | 4
R4 | Insurance or cost question | 2
R5 | Feeling better or concern resolved | 1
R6 | Other or unknown | 3
Notes: Copy the D2 formula down for each reason row. E1 is the monthly total. Illustrative counts only.

## Rollout checklist
Phase | Action | Owner | Target week | Done (Yes/No) | Evidence
Phase 1 setup | Collect baseline no-show log for 2 weeks | Office manager | Week 1-2 | No | Log sheet
Phase 1 setup | Load message scripts into reminder system | Front desk lead | Week 2 | No | System export
Phase 2 pilot | Start 3-touch sequence for one provider | Office manager | Week 3-6 | No | Tracker sheet
Phase 3 expand | Add waitlist backfill routine | Front desk lead | Week 7-10 | No | Waitlist log
Phase 3 expand | Review reason codes and adjust send times | Office manager | Week 11-13 | No | Summary sheet
Notes: G1 shows share complete. Work phases in order. Illustrative rows only.