## scope_register
Request ID (illustrative) | Date received | Request description | In-scope / Out-of-scope | Related deliverable (D-number) | Action taken | Change order ref | Minutes spent | Billed amount
ILL-001 | 2026-02-03 | Illustrative: extra homepage banner variant | Out-of-scope | D2 | Change order sent | CO-ILL-01 | 20
ILL-002 | 2026-02-05 | Illustrative: small text correction within criteria | In-scope | D1 | Courtesy applied and logged |  | 10
Notes: Log every client request the same day. Use In-scope only when the item fits written acceptance criteria. All IDs and rows are illustrative.

## milestone_map
Milestone code (illustrative) | Milestone name | Linked deliverables | Due date | Payment tied to milestone | Entry criteria | Exit criteria | Status
M1-ILL | Illustrative: kickoff and brief lock | D1 | 2026-02-10 | 0 | Brief signed | Acceptance criteria recorded | Done
M2-ILL | Illustrative: draft delivery | D1,D2 | 2026-02-17 | 0 | Client content received | Drafts delivered | In progress
Notes: Each milestone maps to one or more numbered deliverables. No milestone is marked complete until its deliverables meet acceptance criteria.

## change_order_log
Change order ref (illustrative) | Date submitted | Related deliverable | Description | Fee | Schedule impact (days, illustrative) | Status | Date approved | Billed amount
CO-ILL-01 | 2026-02-06 | D2 | Illustrative: additional banner variant | 120 | 2 | Approved | 2026-02-07
CO-ILL-02 | 2026-02-09 | D3 | Illustrative: added format export | 80 | 1 | Pending
Notes: Billed amount counts only when Date approved is filled. Total row at I4 sums billed amounts. All refs and amounts are illustrative.

## revision_counter
Deliverable (D-number) | Rounds included (illustrative) | Round 1 date | Round 2 date (illustrative) | Extra rounds used | Overage rate per round (illustrative) | Extra billed
D1 | 2 | 2026-02-12 | 2026-02-14 | 0 | 60
D2 | 2 | 2026-02-15 |  | 1 | 60
Notes: One row per deliverable. Extra billed equals extra rounds times overage rate. All counts and rates are illustrative.

## rate_card
Service code | Service description | Unit | Rate (illustrative) | Notes
standard | Illustrative: general design revision work | per hour | 60 | Used by scope register lookup
rush | Illustrative: expedited delivery | per hour | 90 | Applies only when rush agreed in writing
Notes: Fill with real rates before use. Example rates are illustrative and must be replaced.