## request_log
Request ref (illustrative) | Date received | Request type (access/deletion) | Requester contact | Identity verified (yes/no) | Scope agreed date | Statutory deadline (computed) | Internal SLA date (computed) | Stage | Days remaining (computed) | Status
DSAR-ILL-01 | 2026-03-02 | access | requester email on file | yes | 2026-03-05 |  |  | Scoped |  | Open
DSAR-ILL-02 | 2026-03-04 | deletion | requester email on file | no |  |  |  | Received |  | Awaiting identity
Notes: Statutory deadline uses 30 business-day computation as a working proxy; verify obligations with qualified counsel since the brief cites 30 days GDPR and 45 days several US states. Internal SLA uses 23 business days. All refs and dates are illustrative.
Formulas:
Statutory deadline (computed) = WORKDAY([Date received],30)
Internal SLA date (computed) = WORKDAY([Date received],23)
Days remaining (computed) = NETWORKDAYS(TODAY(),[Statutory deadline (computed)])

## verification_checklist
Request ref (illustrative) | Check item | Evidence seen | Verified by | Date | Result
DSAR-ILL-01 | Illustrative: government ID matched to account name | ID reference noted, not stored | Support lead | 2026-03-03 | Pass
DSAR-ILL-01 | Illustrative: account email ownership confirmed | Verification link confirmed | Support lead | 2026-03-03 | Pass
Notes: Do not advance to Scoped until identity checks pass. Minimize copies of identity documents.

## source_registry
Source name (illustrative) | Owner | Data categories held | Retention basis | Deletion method | Last reviewed
ILL-DB-main | Engineering | Illustrative: account profile fields | Contract performance | Soft delete then purge per runbook | 2026-02-20
ILL-support-desk | Support | Illustrative: ticket history | Legitimate interest per counsel advice | Ticket anonymization | 2026-02-20
Notes: One row per system that may hold requester data. Review when systems change.

## deletion_runbook_tracker
Request ref (illustrative) | Source | Action required | Assigned to | Due date (illustrative) | Evidence of completion | Done
DSAR-ILL-02 | ILL-DB-main | Illustrative: delete profile row | Engineer on duty | 2026-03-20 | Ticket number noted | No
DSAR-ILL-02 | ILL-backups | Illustrative: confirm expiry on rotation | Engineer on duty | 2026-03-22 | Backup log noted | No
Notes: Track per-source deletion steps. Backups and logs need special handling per runbook.

## sla_dashboard
Metric (computed) | Value | Notes
Open requests |  | Count of rows with Status Open
Due within 5 business days (illustrative threshold) |  | Uses Days remaining column
Overdue (past statutory deadline proxy) |  | Requires immediate review with counsel
Notes: Dashboard counts read from request_log. Thresholds are illustrative working aids, not legal determinations.