## permit_register
Item | Issuing office | Applies (yes/no/verify) | Dependency | Illustrative low | Illustrative high | Verified fee | Notes
Business entity registration | State registrar - verify locally | yes | None - file first | 50 | 300 |  | Illustrative range only - verify with issuing agency
Health plan review | County health office - verify locally | yes | After commissary letter | 100 | 600 |  | Illustrative range only - verify with issuing agency
City vendor permit | City vending office - verify locally | yes | After health and fire approvals | 100 | 800 |  | Illustrative range only - verify with issuing agency
Notes: All cost figures are illustrative ranges only for learning structure. Never pay from illustrative figures. Verify every fee and form with the issuing agency and enter verified fees with dates. Totals are formula sums. Illustrative rows only.

## timeline_planner
Item | Dependency status | Quoted lead-time days | Earliest start | Planned filing date | Expected decision date | Buffer days | Critical path flag
Certification course | No dependency | 14 | Week 1 | Week 1 day 1 |  | 3 | Parallel
Health plan review | Needs commissary letter | 14 | Week 3 | Week 3 day 1 | Week 5 | 5 | Sequential
City vendor permit | Needs health and fire approvals | 10 | Week 5 | Week 5 day 3 | Week 7 | 5 | Sequential
Notes: Quoted lead times are entered only after agency confirmation with verification dates in the tracker. Parallel items run together; sequential items stack. Typical full-stack planning context is 4 to 10 weeks; your case depends on backlog and readiness. Illustrative rows only.

## application_tracker
Item | Agency | Packet complete (yes/no) | Filing date | Receipt number | Quoted lead time | Follow-up date | Contact and notes | Result | Approval date | Expiration date
Health plan review | County health office | yes | 2026-04-07 | Illustrative receipt R-1001 | 14 days | 2026-04-21 | Counter visit, staff name logged | Approved with one correction | 2026-04-21 | 2027-04-21
Fire inspection | Fire authority | yes | 2026-04-22 | Illustrative receipt R-1002 | 7 days | 2026-04-29 | Onboard inspection scheduled | Passed | 2026-04-28 | 2027-04-28
Notes: Log filings the same day with receipt numbers and follow-up dates. Never leave a pending row without a next date. Record inspector names, results, and corrections factually. Receipt numbers shown are illustrative only.

## renewal_calendar
Approval item | Agency | Approval date | Expiration date | Renewal lead time days | Admin buffer days | Alert date | Renewal filed date | Status
Health permit | County health office | 2026-04-21 | 2027-04-21 | 30 | 7
City vendor permit | City vending office | 2026-05-05 | 2027-05-05 | 30 | 7 | 2027-03-29 |  | Current
Notes: Alert date equals expiration minus lead time minus buffer by formula. Review monthly, weekly within 30 days of expiration. One row per approval per jurisdiction. Illustrative dates only.
Formulas:
Status = IF([Renewal filed date]<>"","Filed",IF(TODAY()>=[Expiration date],"Overdue",IF(TODAY()>=[Alert date],"Due soon","Current")))

## inspection_checklist
Check group | Check item | Ready (yes/no) | Verified date | Notes
Truck | Fresh water filled, hot water verified at tap | yes | 2026-04-27 | Tested under load day before
Truck | Cold-holding verified with calibrated thermometers | yes | 2026-04-27 | Separate raw and ready-to-eat storage labeled
Documents | Commissary letter plus certification cards on board | yes | 2026-04-27 | Ordered per packet checklist
Staff | Certified person present, demonstrations rehearsed | yes | 2026-04-27 | Handwash, temperature, waste routine ready
Notes: Complete the day before inspection. Bring documents in packet order. Log inspection date, inspector name, result, and corrections in the tracker the same day. Illustrative rows only.