## Start Here
Renovation Allowance & Change-Order Control
This workbook answers one question your budget spreadsheet cannot: what will this project actually cost me, given what I have already signed and what I still owe back?
How to use it
1. Setup - project name, contingency reserve, currency. Ten minutes.
2. Cost Control - one row per budget line. Type the original budget and what you have signed. The rest is calculated.
3. Payments - every payment, one row. 'Paid to date' on Cost Control is summed from here, never typed.
4. Change Orders - every change with its own number. Only rows marked Approved count, and they raise the revised budget automatically.
5. Allowances - items priced as a spending allowance before the actual product is chosen (tile, lighting, counters). This sheet is where silent overruns and forgotten credits show up.
6. Contingency - the reserve and what has been drawn from it. It is not a slush fund.
7. Summary - the four numbers that matter, plus checks that tell you what to fix.
8. Assumptions - write down what is excluded. An estimate is only honest with its exclusions next to it.
Colour code
White cells: you fill them in. Blue cells: calculated - do not overwrite. Yellow rows: EXAMPLE data - overwrite or delete them.
What this workbook is not
It is not legal, tax or financial advice, and it does not replace your contract. Allowance, change-order and payment terms are governed by the contract you signed - check it, and check with a qualified professional where the stakes justify it.
A note on the example numbers
The yellow rows describe a $45,000 kitchen renovation that ends up projected $6,500 over its revised budget. The guide walks through exactly those numbers. Delete the examples once you understand them.

## Setup
Setting | Your value | Notes
Project name | Kitchen renovation (EXAMPLE) | Anything you will recognise later
Property address |  | Optional
Currency symbol | $ | Used in the labels only
Contingency reserve (USD) | 4500 | EXAMPLE: 10% of a $45,000 line budget. Research puts 10-20% as a floor and 25-30% for structural work.
Today's date | 2026-06-20 | Update when you review the sheet
Who approves change orders | Owner | Write the name, not the role, if more than one person can approve
Who approves contingency draws | Owner | Same: a name
Review cadence | Monthly, plus after every signed change order | The review is what makes the numbers true

## Cost Control
Line | Category | What it covers | Original budget | Original committed | Approved changes | Revised budget | Committed total | Paid to date | Unpaid committed | Forecast to complete | Projected final | Variance vs revised | Status
K-01 | Demolition | Strip kitchen, remove a non-load-bearing partition | 3000 | 2800 | [5 empty] | 0
K-02 | Millwork | Cabinet package, delivered and installed | 12000 | 12500 | [5 empty] | 0
K-03 | Surfaces | Countertop allowance, made when the slab was chosen | 7500 | 7500 | [5 empty] | 0
K-04 | Tile & flooring | Floor tile plus installation labour | 6000 | 5900 | [5 empty] | 550
K-05 | Electrical | Rewire, plus one added circuit (change order) | 4500 | 4800 | [5 empty] | 0
K-06 | Paint & finish | Painting and trim, not yet contracted | 3000 | 0 | [5 empty] | 3750
K-07 | Design & permits | Design fee and building permit | 1200 | 1200 | [5 empty] | 0
K-08 | Appliances | Range, hood, dishwasher - not ordered yet | 5000 | 0 | [5 empty] | 5600
K-09 | Other | Project management fee | 2800 | 2800 | [5 empty] | 0

## Change Orders
CO # | Date | Line | What changed | Amount | Approved? | Amount that counts
CO-01 | 2026-05-20 | K-03 | Countertop selection above the allowance | 1700 | Yes
CO-02 | 2026-06-04 | K-05 | Added kitchen circuit required by inspection | 600 | Yes
CO-03 | 2026-06-18 | K-06 | Upgraded paint finish - not signed yet | 450 | No

## Allowances
Allowance # | Line | Item | Allowance in contract | Chosen selection | Difference | Credit already received | Credit still owed to you | Change order # | Status
A-01 | K-03 | Countertops | 7500 | 9200 |  | 0 |  | CO-01
A-02 | K-06 | Lighting | 1200 | 400 |  | 300
A-03 | K-05 | Plumbing fixtures | 1500 | 1900 |  | 0

## Payments
Date | Line | Paid to | Amount | Method | Note
2026-05-06 | K-01 | Demo crew | 1400 | Bank transfer | 50% deposit
2026-05-18 | K-02 | Cabinet supplier | 6250 | Card | 50% on order
2026-05-22 | K-03 | Stone fabricator | 2250 | Bank transfer | 30% on template
2026-06-01 | K-05 | Electrician | 2400 | Bank transfer | First invoice
2026-05-02 | K-07 | City permits office | 1200 | Card | Permit issued
2026-06-02 | K-09 | Project manager | 2800 | Bank transfer | Final fee

## Contingency
Date | What the reserve paid for | Amount | Approved by | Note | Reserve remaining | Drawn so far
2026-05-12 | Hidden rot behind the sink wall | 900 | Owner | Photos filed
2026-06-03 | Code-required outlet upgrade | 1200 | Owner | Electrician letter filed

## Assumptions
# | Type | Statement | Where it lives | Owner's note
1 | Excluded | Temporary storage and rental furniture | Not in any line | Add a line if this becomes real
2 | Excluded | Landscaping and exterior work | Out of scope this phase
3 | Assumption | Owner supplies appliances at retail price |  | Quotes may move
4 | Allowance | Countertops priced at $7,500 until the slab is chosen | A-01 | Reconcile in Allowances
5 | Risk | House built before 1980 - hidden conditions likely |  | Reserve sized at 10%; structural work may justify 25-30%

## Summary
Renovation cost control - summary
Original budget (sum of lines)
Approved change orders
Revised budget
Committed total
Paid to date
Unpaid committed
Forecast to complete
Projected final cost
Variance vs revised budget
Committed as % of revised budget
Contingency reserve remaining
Allowance overruns (all)
Allowance credits still owed to you
Change orders awaiting signature
Lines already over their revised budget
All-in plan (revised budget + reserve)
Checks - fix anything that is not OK
Any payment recorded against a line that does not exist?
Any allowance overage with no approved change order?
Paid more than committed on any line?
Projected final over revised budget?
Contingency reserve exhausted?
Remaining spend larger than what is left in the revised budget?
Any change order still marked No?
Any line with no original budget?
Blue cells are formulas. If a number looks wrong, check the row it came from - never overwrite a total.